## Gantt Chart (Master Schedule)
CARLOS HILADO MEMORIAL STATE UNIVERSITY — COLLEGE OF COMPUTER STUDIES
CAPSTONE PROJECT GANTT CHART: INTEGRATED POS-DRIVEN INVENTORY WITH DATA ANALYTICS FOR TARGETING SALES MARKETING
Timeline: May 5, 2026 to October 10, 2026 (159 Calendar Days / 23 Weeks) ¦ SDLC: V-Model ¦ Directive: Testing Phase has the Highest Work Allocation
WBS / ID | Task Description & Activity Milestones | Lead Role | Start Date | End Date | Days | Predecessor | Critical? | May 2026 (May 5-31) |  |  |  | June 2026 (Jun 1-30) |  |  |  | July 2026 (Jul 1-31) |  |  |  | August 2026 (Aug 1-31) |  |  |  | September 2026 (Sep 1-30) |  |  |  | October 2026 (Oct 1-10) |  | Legend
[8 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2
1.0 | PHASE I: PLANNING & REQUIREMENTS ANALYSIS | Team / Analyst | 2026-05-05 | 2026-05-25 | 21 |  | YES | [22 empty] | PHASE | bar: May 2026 (May 5-31) W1 to May 2026 (May 5-31) W3
A | Requirements Elicitation & Stakeholder Interviews | Team / PM | 2026-05-05 | 2026-05-18 | 14 | - | YES | [22 empty] | CRITICAL | bar: May 2026 (May 5-31) W1 to May 2026 (May 5-31) W2
B | Process Observation & Inventory Workflow Audit | System Analyst | 2026-05-10 | 2026-05-25 | 16 | A (SS+5d) | YES | [22 empty] | CRITICAL | bar: May 2026 (May 5-31) W2 to May 2026 (May 5-31) W3
2.0 | PHASE II: SYSTEM & ARCHITECTURAL DESIGN | System Analyst | 2026-05-20 | 2026-06-18 | 30 |  | YES | [22 empty] | PHASE | bar: May 2026 (May 5-31) W3 to June 2026 (Jun 1-30) W3
C | UI/UX Wireframing, DFDs (Levels 0-2) & ERD Modeling | System Analyst | 2026-05-20 | 2026-06-04 | 16 | B | YES | [22 empty] | CRITICAL | bar: May 2026 (May 5-31) W3 to June 2026 (Jun 1-30) W1
D | System Architecture & Security Design (JWT, pgcrypto) | System Analyst | 2026-05-26 | 2026-06-10 | 16 | C | YES | [22 empty] | CRITICAL | bar: May 2026 (May 5-31) W4 to June 2026 (Jun 1-30) W2
E | Predictive Analytics Ensemble & Promotions Design | System Analyst | 2026-06-01 | 2026-06-18 | 18 | D | NO | [22 empty] | FLOAT | bar: June 2026 (Jun 1-30) W1 to June 2026 (Jun 1-30) W3
3.0 | PHASE III: DETAILED MODULE SPECIFICATIONS | System Analyst | 2026-06-12 | 2026-07-03 | 22 |  | YES | [22 empty] | PHASE | bar: June 2026 (Jun 1-30) W2 to July 2026 (Jul 1-31) W1
F | Master Footwear Catalog & Inventory Parameters Design | System Analyst | 2026-06-12 | 2026-06-25 | 14 | D | YES | [22 empty] | CRITICAL | bar: June 2026 (Jun 1-30) W2 to June 2026 (Jun 1-30) W3
G | POS Terminal, Multi-Tender & Receipt Design | System Analyst | 2026-06-15 | 2026-06-28 | 14 | F | YES | [22 empty] | CRITICAL | bar: June 2026 (Jun 1-30) W3 to June 2026 (Jun 1-30) W4
H | Replacement Intake, Camera QR & Audit Trail Design | System Analyst | 2026-06-18 | 2026-07-03 | 16 | G | YES | [22 empty] | CRITICAL | bar: June 2026 (Jun 1-30) W3 to July 2026 (Jul 1-31) W1
4.0 | PHASE IV: CODING & IMPLEMENTATION | Programmer | 2026-06-28 | 2026-08-10 | 44 |  | YES | [22 empty] | PHASE | bar: June 2026 (Jun 1-30) W4 to August 2026 (Aug 1-31) W2
I | Database Setup, RLS Policies & Cloud Storage Buckets | Programmer | 2026-06-28 | 2026-07-12 | 15 | F, G, H | YES | [22 empty] | CRITICAL | bar: June 2026 (Jun 1-30) W4 to July 2026 (Jul 1-31) W2
J | Front-End UI Development (React, TypeScript, Tailwind) | Programmer | 2026-07-04 | 2026-07-27 | 24 | I | NO | [22 empty] | FLOAT | bar: July 2026 (Jul 1-31) W1 to July 2026 (Jul 1-31) W4
K | Back-End API Services & Session Cryptography | Programmer | 2026-07-08 | 2026-07-31 | 24 | I | YES | [22 empty] | CRITICAL | bar: July 2026 (Jul 1-31) W2 to July 2026 (Jul 1-31) W4
L | Core POS Checkout, Barcode & Thermal Receipt Engine | Programmer | 2026-07-15 | 2026-08-05 | 22 | J, K | YES | [22 empty] | CRITICAL | bar: July 2026 (Jul 1-31) W3 to August 2026 (Aug 1-31) W1
M | Predictive Sales Forecasting & Brevo Marketing Blast | Programmer | 2026-07-20 | 2026-08-10 | 22 | L | YES | [22 empty] | CRITICAL | bar: July 2026 (Jul 1-31) W3 to August 2026 (Aug 1-31) W2
N | Replacement Intake & Hardware Camera QR Scanner | Programmer | 2026-07-22 | 2026-08-10 | 20 | L | YES | [22 empty] | CRITICAL | bar: July 2026 (Jul 1-31) W4 to August 2026 (Aug 1-31) W2
5.0 | PHASE V: TESTING & QUALITY ASSURANCE (HIGHEST DURATION) | Quality Assurance | 2026-07-28 | 2026-09-28 | 63 |  | YES | [22 empty] | PHASE | bar: July 2026 (Jul 1-31) W4 to September 2026 (Sep 1-30) W4
O | Module Unit Testing & Bug Fixes (White-Box Test Cases) | QA / Programmer | 2026-07-28 | 2026-08-18 | 22 | J, K | NO | [22 empty] | FLOAT | bar: July 2026 (Jul 1-31) W4 to August 2026 (Aug 1-31) W3
P | Subsystem & Integration Testing (Realtime Sync & Broadcast) | Quality Assurance | 2026-08-08 | 2026-08-28 | 21 | M, N, O | YES | [22 empty] | CRITICAL | bar: August 2026 (Aug 1-31) W2 to August 2026 (Aug 1-31) W4
Q | Functional Black-Box Testing (Alpha POS, Inventory, Returns) | Quality Assurance | 2026-08-18 | 2026-09-08 | 22 | P | YES | [22 empty] | CRITICAL | bar: August 2026 (Aug 1-31) W3 to September 2026 (Sep 1-30) W2
R | Security, Penetration & Vulnerability Testing (Lockout, RLS) | Quality Assurance | 2026-08-25 | 2026-09-14 | 21 | P | NO | [22 empty] | FLOAT | bar: August 2026 (Aug 1-31) W4 to September 2026 (Sep 1-30) W3
S | Full System, Performance & Hardware Stress Testing | Quality Assurance | 2026-09-01 | 2026-09-20 | 20 | Q, R | YES | [22 empty] | CRITICAL | bar: September 2026 (Sep 1-30) W1 to September 2026 (Sep 1-30) W3
T | Bug Resolution, Retesting & System Hardening | Programmer / QA | 2026-09-10 | 2026-09-28 | 19 | S | YES | [22 empty] | CRITICAL | bar: September 2026 (Sep 1-30) W2 to September 2026 (Sep 1-30) W4
U | ISO/IEC 25010:2011 Software Evaluation (Experts & Users) | Team / QA | 2026-09-15 | 2026-09-28 | 14 | S | YES | [22 empty] | CRITICAL | bar: September 2026 (Sep 1-30) W3 to September 2026 (Sep 1-30) W4
6.0 | PHASE VI: USER ACCEPTANCE, DEPLOYMENT & TURNOVER | Team / PM | 2026-09-26 | 2026-10-10 | 15 |  | YES | [22 empty] | PHASE | bar: September 2026 (Sep 1-30) W4 to October 2026 (Oct 1-10) W2
V | Beta Testing & User Acceptance Testing (UAT with Client) | Team / PM | 2026-09-26 | 2026-10-03 | 8 | T, U | YES | [22 empty] | CRITICAL | bar: September 2026 (Sep 1-30) W4 to October 2026 (Oct 1-10) W1
W | Client Feedback Integration & UI Final Polish | Programmer | 2026-10-01 | 2026-10-06 | 6 | V | YES | [22 empty] | CRITICAL | bar: October 2026 (Oct 1-10) W1 to October 2026 (Oct 1-10) W2
X | Final Documentation, User Manual & Project Turnover | Team | 2026-10-04 | 2026-10-10 | 7 | W | YES | [22 empty] | CRITICAL | bar: October 2026 (Oct 1-10) W1 to October 2026 (Oct 1-10) W2
TOTAL PROJECT DURATION (MAY 5 TO OCTOBER 10, 2026) |  |  |  |  | 159 Days
GANTT CHART COLOR LEGEND:
■ Red Bars = Critical Path Activities (Zero Float - Direct Impact on Project Delivery)
■ Blue Bars = Non-Critical / Flexible Float Activities
■ Dark Green = SDLC Phase Summary Bars
★ HIGHEST WORK ALLOCATION: Phase 5 Testing & Quality Assurance spans 63 calendar days (39.6% of project).

## PERT-CPM (Critical Path)
CARLOS HILADO MEMORIAL STATE UNIVERSITY — COLLEGE OF COMPUTER STUDIES
APPENDIX I: PROGRAM EVALUATION REVIEW TECHNIQUE - CRITICAL PATH METHOD (PERT-CPM)
Meryl Shoes Enterprise System ¦ Critical Path: A → B → C → D → F → G → H → I → K → L → M/N → P → Q → S → T/U → V → W → X (159 Days)
Activity ID | Task / Milestone Name | Lead Role | Predecessors | Duration (D) | Early Start (ES) | Early Finish (EF) | Late Start (LS) | Late Finish (LF) | Slack / Float (S) | Critical Path?
A | Requirements Elicitation & Interviews | Team / PM | None | 14 | Day 0 (May 05) | Day 14 (May 18) | Day 0 (May 05) | Day 14 (May 18) | 0 | CRITICAL
B | Process Observation & Inventory Workflow | System Analyst | A (SS+5d) | 16 | Day 5 (May 10) | Day 21 (May 25) | Day 5 (May 10) | Day 21 (May 25) | 0 | CRITICAL
C | UI/UX Wireframes, DFD (0-2) & ERD | System Analyst | B | 16 | Day 15 (May 20) | Day 31 (Jun 04) | Day 15 (May 20) | Day 31 (Jun 04) | 0 | CRITICAL
D | System Architecture & Security Design | System Analyst | C | 16 | Day 21 (May 26) | Day 37 (Jun 10) | Day 21 (May 26) | Day 37 (Jun 10) | 0 | CRITICAL
E | Analytics Modeling & Promotions Design | System Analyst | D | 18 | Day 27 (Jun 01) | Day 45 (Jun 18) | Day 29 (Jun 03) | Day 47 (Jun 20) | 2 | FLOAT
F | Catalog & Inventory Parameters Design | System Analyst | D | 14 | Day 38 (Jun 12) | Day 52 (Jun 25) | Day 38 (Jun 12) | Day 52 (Jun 25) | 0 | CRITICAL
G | POS Terminal, Multi-Tender & Receipt Design | System Analyst | F | 14 | Day 41 (Jun 15) | Day 55 (Jun 28) | Day 41 (Jun 15) | Day 55 (Jun 28) | 0 | CRITICAL
H | Replacement Intake & Camera QR Design | System Analyst | G | 16 | Day 44 (Jun 18) | Day 60 (Jul 03) | Day 44 (Jun 18) | Day 60 (Jul 03) | 0 | CRITICAL
I | DB Setup, RLS Policies & Cloud Buckets | Programmer | F, G, H | 15 | Day 54 (Jun 28) | Day 69 (Jul 12) | Day 54 (Jun 28) | Day 69 (Jul 12) | 0 | CRITICAL
J | Front-End UI Development (React/TS) | Programmer | I | 24 | Day 60 (Jul 04) | Day 84 (Jul 27) | Day 62 (Jul 06) | Day 86 (Jul 29) | 2 | FLOAT
K | Back-End APIs & Session Cryptography | Programmer | I | 24 | Day 64 (Jul 08) | Day 88 (Jul 31) | Day 64 (Jul 08) | Day 88 (Jul 31) | 0 | CRITICAL
L | Core POS Checkout & Thermal Receipt Engine | Programmer | J, K | 22 | Day 71 (Jul 15) | Day 93 (Aug 05) | Day 71 (Jul 15) | Day 93 (Aug 05) | 0 | CRITICAL
M | Predictive Analytics & Brevo Email Blast | Programmer | L | 22 | Day 76 (Jul 20) | Day 98 (Aug 10) | Day 76 (Jul 20) | Day 98 (Aug 10) | 0 | CRITICAL
N | Replacement Intake & Camera QR Module | Programmer | L | 20 | Day 78 (Jul 22) | Day 98 (Aug 10) | Day 78 (Jul 22) | Day 98 (Aug 10) | 0 | CRITICAL
O | Module Unit Testing (White-Box Test Cases) | QA / Dev | J, K | 22 | Day 84 (Jul 28) | Day 106 (Aug 18) | Day 86 (Jul 30) | Day 108 (Aug 20) | 2 | FLOAT
P | Integration Testing & Realtime Sync | Quality Assurance | M, N, O | 21 | Day 95 (Aug 08) | Day 116 (Aug 28) | Day 95 (Aug 08) | Day 116 (Aug 28) | 0 | CRITICAL
Q | Functional Black-Box Alpha Testing | Quality Assurance | P | 22 | Day 105 (Aug 18) | Day 127 (Sep 08) | Day 105 (Aug 18) | Day 127 (Sep 08) | 0 | CRITICAL
R | Security, Penetration & Vulnerability Tests | Quality Assurance | P | 21 | Day 112 (Aug 25) | Day 133 (Sep 14) | Day 113 (Aug 26) | Day 134 (Sep 15) | 1 | FLOAT
S | Full System & Stress/Hardware Tests | Quality Assurance | Q, R | 20 | Day 119 (Sep 01) | Day 139 (Sep 20) | Day 119 (Sep 01) | Day 139 (Sep 20) | 0 | CRITICAL
T | Bug Resolution & System Hardening | Programmer / QA | S | 19 | Day 128 (Sep 10) | Day 147 (Sep 28) | Day 128 (Sep 10) | Day 147 (Sep 28) | 0 | CRITICAL
U | ISO/IEC 25010:2011 Software Evaluation | Team / QA | S | 14 | Day 133 (Sep 15) | Day 147 (Sep 28) | Day 133 (Sep 15) | Day 147 (Sep 28) | 0 | CRITICAL
V | User Acceptance Testing (UAT with Client) | Team / PM | T, U | 8 | Day 144 (Sep 26) | Day 152 (Oct 03) | Day 144 (Sep 26) | Day 152 (Oct 03) | 0 | CRITICAL
W | User Feedback Integration & UI Polish | Programmer | V | 6 | Day 149 (Oct 01) | Day 155 (Oct 06) | Day 149 (Oct 01) | Day 155 (Oct 06) | 0 | CRITICAL
X | Final Documentation & System Turnover | Team | W | 7 | Day 152 (Oct 04) | Day 159 (Oct 10) | Day 152 (Oct 04) | Day 159 (Oct 10) | 0 | CRITICAL
TOTAL CRITICAL PATH DURATION |  |  |  | 159 Days | Zero Float (S = 0) Chain Controls Project Turnover Date (October 10, 2026)

## Phase Allocation & Testing Time
CARLOS HILADO MEMORIAL STATE UNIVERSITY — COLLEGE OF COMPUTER STUDIES
SDLC PHASE ALLOCATION ANALYSIS & PROFESSOR'S DIRECTIVE VERIFICATION
Verification that the Testing & Quality Assurance Phase has the HIGHEST Duration and Work Effort
SDLC Phase | Phase Description | Calendar Date Range | Elapsed Days | Cumulative Task-Days | % of Calendar Span | Work Allocation Rank
Phase 1 | Planning & Requirements Elicitation | May 05, 2026 – May 25, 2026 | 21 | 30 | 13.2% | Rank 5
Phase 2 | System & Architectural Design | May 20, 2026 – June 18, 2026 | 30 | 50 | 18.9% | Rank 3
Phase 3 | Module Detailed Specifications | June 12, 2026 – July 03, 2026 | 22 | 44 | 13.8% | Rank 4
Phase 4 | Coding & System Implementation | June 28, 2026 – August 10, 2026 | 44 | 127 | 27.7% | Rank 2
Phase 5 | Testing & Quality Assurance | July 28, 2026 – September 28, 2026 | 63 | 139 | 39.6% | RANK 1 (HIGHEST WORK)
Phase 6 | Acceptance, Deployment & Closeout | September 26, 2026 – October 10, 2026 | 15 | 21 | 9.4% | Rank 6
TOTAL ENTIRE PROJECT LIFECYCLE |  |  | 159 Days | 411 Task-Days | 100.0% | 23 Calendar Weeks
DETAILED BREAKDOWN OF TESTING & QUALITY ASSURANCE ACTIVITIES (PHASE 5)
Test ID | Testing Activity & Scope | Testing Method / Tool | Start Date | End Date | Days | Evaluators / Lead
Task O | Module-Based Unit Testing & Cryptography Validation | White-Box / Pest PHP & pytest | 2026-07-28 | 2026-08-18 | 22 | QA / Programmer
Task P | Subsystem & Cross-Tab Integration Testing | BroadcastChannel & Supabase Realtime | 2026-08-08 | 2026-08-28 | 21 | Quality Assurance
Task Q | Functional Black-Box Alpha Testing (POS, Sizing, Returns) | Cypress / Black-Box Test Cases | 2026-08-18 | 2026-09-08 | 22 | Quality Assurance
Task R | Security, Brute-Force & Vulnerability Testing | Penetration Testing / RLS Check | 2026-08-25 | 2026-09-14 | 21 | Quality Assurance
Task S | Full System, Performance & Hardware Stress Testing | Concurrency & Hardware Scanners | 2026-09-01 | 2026-09-20 | 20 | Quality Assurance
Task T | Bug Resolution, Retesting & System Hardening | Regression Test Cycles | 2026-09-10 | 2026-09-28 | 19 | Programmer / QA
Task U | ISO/IEC 25010:2011 Software Product Quality Evaluation | 5-Point Likert Questionnaire | 2026-09-15 | 2026-09-28 | 14 | 5 IT Experts + 20 Users

## PERT Network Diagram
MERYL SHOES SYSTEM — PERT NETWORK DIAGRAM (APPENDIX I)
Critical Path Duration: 159 Calendar Days (May 5 – Oct 10, 2026) ¦ Chain: A → B → C → D → F → G → H → I → K → L → M/N → P → Q → S → T/U → V → W → X

## CPM Network Diagram
MERYL SHOES SYSTEM — CRITICAL PATH METHOD (CPM) NETWORK DIAGRAM
Detailed ES, EF, LS, LF, Duration (D), and Float/Slack [S] per Activity Node